## Sheet1
Name | Hours | Rate | Total Cost | Complexity | Contingency | Assigned Role
User Management | 40 hours | $100/hour (industry rate for Backend Developer) | $4,000 | Medium | 10% buffer (=$400) | Backend Developer
Create Ticket with Category | 30 hours | $100/hour (industry rate for Frontend Developer) | $3,000 | Medium | 10% buffer (=$300) | Frontend Developer
Attach Files/Screenshots | 20 hours | $100/hour (industry rate for Backend Developer) | $2,000 | Low | 5% buffer (=$100) | Backend Developer
Automatic Ticket Assignment | 50 hours | $100/hour (industry rate for Backend Developer) | $5,000 | High | 15% buffer (=$750) | Backend Developer
Track Ticket Status | 40 hours | $100/hour (industry rate for Backend Developer) | $4,000 | Medium | 10% buffer (=$400) | Backend Developer
Email Notifications for Ticket Updates | 30 hours | $100/hour (industry rate for Frontend Developer) | $3,000 | Medium | 10% buffer (=$300) | Frontend Developer
SLA Breach Alerts | 40 hours | $100/hour (industry rate for Backend Developer) | $4,000 | Medium | 10% buffer (=$400) | Backend Developer
Dashboard with Metrics | 60 hours | $100/hour (industry rate for Frontend Developer) | $6,000 | High | 15% buffer ($900) | Frontend Developer
Export Reports (CSV) | 20 hours | $100/hour (industry rate for Backend Developer) | $2,000 | Low | 5% buffer ($100) | Backend Developer
Integration with Email Service | 50 hours | $100/hour (industry rate for Frontend Developer) | $5,000 | High | 15% buffer ($750) | Frontend Developer
Integration with Internal HR System for User Data | 60 hours | $100/hour (industry rate for Backend Developer) | $6,000 | High | 15% buffer ($900) | Backend Developer
Secure Authentication (OAuth2) | 80 hours | $100/hour (industry rate for Backend Developer) | $8,000 | High | 15% buffer ($1,200) | Backend Developer