## Sheet1
Name | Description | Priority | Type | Dependencies | Assignee
User Management | Implement role-based access control for employees, agents, and admins. | Medium | Feature | None | Backend Developer (Admin can manage users and roles)
Create Ticket with Category | Allow users to create tickets with assigned categories (Hardware, Software, Access, Network). | High | Feature | User Management | Frontend Developer
Attach Files/Screenshots | Enable users to attach files and screenshots to their tickets. | Medium | Feature | Create Ticket with Category | Backend Developer
Automatic Ticket Assignment | Automatically assign tickets based on category (Hardware, Software, Access, Network). | High | Feature | Create Ticket with Category | Backend Developer
Track Ticket Status | Implement ticket status tracking (Open, In Progress, Resolved, Closed). | Medium | Feature | Create Ticket with Category | Backend Developer
Email Notifications for Ticket Updates | Send email notifications to users and agents on ticket updates. | High | Feature | Track Ticket Status | Frontend Developer
SLA Breach Alerts | Implement alerts for SLA breaches. | Medium | Feature | Track Ticket Status | Backend Developer
Dashboard with Metrics | Create a dashboard displaying metrics (open tickets, SLA compliance, resolution time). | High | Feature | Reporting | Frontend Developer
Export Reports (CSV) | Allow users to export reports in CSV format. | Medium | Feature | Reporting | Backend Developer
Integration with Email Service | Integrate the ticketing system with an email service. | High | Integration | None | Frontend Developer
Integration with Internal HR System for User Data | Integrate the ticketing system with the internal HR system for user data. | Medium | Integration | None | Backend Developer
Secure Authentication (OAuth2) | Implement secure authentication using OAuth2. | High | Non-Functional Requirement | None | Backend Developer